## Sheet1
MINISTRY OF COMMERCE AND INDUSTRY, 2019 FISCAL YEAR
PROCUREMENT PLAN FOR THE YEAR 2018
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenses At:(Provided Dates) | Actual Expenditure Amount | Balance At: (Provided Dates) | Balance Amount | Comment
1 | Works | 112893 | Construction of one storey building of 48 shops block (A) at the international market Abakaliki | EBS/SCPP/LOA/III/383 | 22001001/ 23020123/ 120000001 | - |  | 3000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 | 2019 | 103148260 | NIL | NIL | Completed
2 | Works | 112893 | 48 shops block (B) | EBS/SCPP/LOA/III/384 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
3 | Works | 112893 | 48 shops block (C) | EBS/SCPP/LOA/III/385 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
4 | Works | 112893 | 48 shops block (D) | EBS/SCPP/LOA/III/386 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
5 | Works | 112893 | 48 shops block (E) | EBS/SCPP/LOA/III/387 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-03 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
6 | Works | 112893 | 48 shops block (F) | EBS/SCPP/LOA/III/388 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
7 | Works | 112893 | 48 shops block (G) | EBS/SCPP/LOA/III/389 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
8 | Works | 112893 | 48 shops block (H) | EBS/SCPP/LOA/III/390 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-03 | 2019-01-18 | 2019-02-20 | 12Months | 294885085.75 |  | 103148260 | NIL | NIL | Completed
9 | Works | 112893 | 48 shops block (I) | EBS/SCPP/LOA/III/391 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed
10 | Works | 112893 | 48 shops block (J) | EBS/SCPP/LOA/III/392 | - do- | - |  |  | Budgetary Provision | Yes | Open Competitive Tendering | 2018-12-01 | 2019-01-18 | 2019-02-20 | 12Months | 103148260 |  | 103148260 | NIL | NIL | Completed