## Sheet1
MINISTRY OF WORK AND TRANSPORT, 2020 FISCAL YEAR
PROCUREMENT PLAN FOR THE YEAR 2020
| Procuring Entry Name | Ministry of Work And Transport, 2020 Fiscal Year
2 | Procurement Plan for the Year | 2020
3 | Version
4 | Date Last Updated
5 | Comment
6
7
| Class | UNSPSC (Project Classification) | Description | Ref No | Project Code | Unit of Measurement | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication | Estimated Dates Award Project Start |  | Project Completion | Revised Budget Amount | Actual Expenses At:(Provided Dates) | Actual Expenditure Amount | Balance At: (Provided Dates) | Balance Amount | Comment
1 | Works | 72141000 | Construction of Enyibichiri Ojon Nwida Road (5km) phase 1 for food production – COVID-19 Economic Recovery | EBS/SCPP/LOA/IV/458 | 34001001/ 23020118/ 17000078 | 5KM | 5km | 500000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2019-11-29 | 2020-01-31 | 2020-02-24 | 12Months | 500000000 | 2020 | 502035056.63 | NIL | NIL | Completed
2 | Works | 72141000 | Construction of Agubia – Abim Aronge Item Amagu Agricultural Road (5km) for food production COVID-19 – Economic Recovery | EBS/SCPP/LOA/IV/459 | 34001001/ 23020118/ 17000043 | 5KM | 5km | 500000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2019-11-13 | 2020-01-31 | 2020-02-28 | 12Months | 7045000 | 2020 | 512174875.88 | NIL | NIL | Completed
3 | Works | 72141000 | Construction of Oferekpe Obvudechi – Oyege Road (5km) | EBS/SCPP/LOA/IV/500 | 34001001/ 23020118/ 17000007 | 5KM | 5km | 500000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2019-11-15 | 2020-01-31 | 2020-04-21 | 12Months | 500000000 | 2020 | 546569631.18 | NIL | NIL | Completed
4 | Works | 72141000 | Construction of MPU Road to Junction of Obiozara Federal Road (10km) | EBS/SCPP/LOA/IV/512 | 3400100/ 23020118/ 17000069 | 10KM | 10km | 1000000000 | Budgetary Provision | Yes | Open Competitive Tendering | 2019-04-20 | 2020-06-01 | 2020-07-28 | 12Months | 2400000000 | 2020 | 2393390127.98 | NIL | NIL | Completed
5 | Works | 72141000 | Construction of 2.73km Boundary / Peripheral road of the Margret Umahi Market International Market. | EBS/SCPP/LOA/IV/514 | - | 2.73km | 2.73km | 2000000000 | Budgetary Provision | Yes | e-procurement | 2019-06-15 | 2020-07-23 |  | 12Months | Not in the budget | 2020 | - | - | - | -
6 | Works | 72141000 | Review of contract sum and swipe of works for the construction of GTC Agba – Agbulu – Eguenu Isu road from (10.3 – 4km). | EBS/SCPP/LOA/IV/516 | 34001001/ 230200114/ 17000033 | 10.3km to 4km | 10.3km to 4km | 500000000 | Budgetary Provision | Yes | Open competitive Tendering | 2020-03-25 | 2020-08-05 | 2020-09-03 | 12Months | 500000000 | 2020 | 589576108.5 | NIL | NIL | Completed
7 | Works | 72141000 | Re- construction of Amasiri Owute Oso Edda Road from Ekoli to Nguzu (5.45). | EBS/SCPP/LOA/IV/519 | 34001001/ 230220114/ 17000014 | 5.45km | 5.45km | 500000000 | Budgetary Provision | Yes | Open competitive Tendering | 2020-07-17 | 2020-09-18 | 2020-10-15 | 12Months | 10000000 | 2020 | 470,457625 | NIL | NIL | Completed
8 | Works | 72141000 | e- award letter for the construction of roads (B,BI,F2,E,H,I,J&K) of Ochudo Centenary City Abakaliki (Length 4.367.781km) | EBS/SCPP/LOA/IV/514 |  | 4367.78km | 4367.78 | - | Budgetary Provision | Yes | Technical | 2020-07-13 | 2020-08-26 | 2020-09-16 | 12Months | - | 2020 | - | - | - | -