## Sheet1
Procuring Entity and Disposing Entity (MDA) | Ministry of Works
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FIRST QUARTER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Constrcution of Enyibichiri Ojon Nwida Agricultural Road (12.4km) in Ikwo LGA for food production - COVID-19 Economic Recovery | 3020114 | Procurement | Works | Shortlisting With Publication Of Expression Of Interest (SLP) |  | State Budget | IKWO | 20000000 | 20000000 | Fixed price contract | 14th Feb 2025 | 17th March 2025 | 17th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 24th march 2025 | 24th march 2025 | 24th march 2025 | 12 Months
Construction of Eworoshade- NdueguAmegu Agricultural Road (5km) for food production | 23020114 | Procurement | Works | Shortlisting With Publication Of Expression Of Interest (SLP) |  | State Budget | IKWO | 2000000000 | 2000000000 | Fixed price contract | 1st Aug. 2025 | 1st Sept 2025 | 1st Sept 2025 |  |  |  | 8th Sept..2025 | 8th Sept..2025 | 9th Sept.2025 | 15th Sept.2025 | 17th Sept.2025 | 12 Months
Construction of Abakaliki Internal Roads | 23020114 | Pre-Qualification | Works | Direct Procurement (DP) |  | State Budget | State Wide | 5000000000 | 5000000000 | Fixed price contract | 2nd Oct. 2025 | 30th Oct 2025 | 30th Oct 2025 |  |  |  | 3rd Nov. .2025 | 3rd Nov. .2025 | 5th Nov..2025 | 5th Nov..2025 | 5th Nov..2025 | 12 Months
The Construction of Agbaja - Ndiebour Access road with Spur to Nkaliki (11.3km | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | Abakaliki | 863800000 | 863800000 | Fixed price contract | 3rd july. 2025 | 1st Aug. 2025 | 1st Aug. 2025 |  |  |  | 4th Aug 2025 | 6th Aug.2025 | 6th Aug.2025 | 18th Aug 2025 | 18th Aug 2025 | 12 Months
Construction of Nkwo Ugwulangwu through Onummahi Nwafor Agbaja to Ehimehi Amelu Okposi with a spur at Eke Okposi (12.6km) | 23020114 | Pre-Qualification | Works | Direct Procurement (DP) |  | State Budget | Ohaozara | 2000000000 | 2000000000 | Fixed price contract | 3rd july. 2025 | 1st Aug. 2025 | 1st Aug. 2025 |  |  |  | 4th Aug 2025 | 6th Aug.2025 | 6th Aug.2025 | 18th Aug 2025 | 18th Aug 2025 | 12 Months
Construction of Umuchima- Nkerefi road with spur to Urobo in Uburu (3.5km) | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | OHAOZARA | 500000000 | 500000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of Court Area- IsinkwoOjigwe- Obuegu Mgbom road (9km) | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | OHAOZARA | 2000000000 | 2000000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
Purchase of 8nos. Of Photocopy machine @ 900,000 | 3010115 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 7200000 | 7200000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Purchase of 3 nos. of 2023 Hilux Van | 23010106 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 150000000 | 150000000 | Fixed price contract | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months | 12 Months
Purchase of 7 no. Laptop @500,000.00 | 23010113 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 3500000 | 3500000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Purchase pf 1no. Complete set of conference table and chair | 3010112 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 1500000 | 1500000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
construction of Ndiechi- OfferekpeAchacha road, Igbeagu, Izzi LGA (29.8KM) | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | IZZI | 2000000000 | 2000000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of Mechanical workshop at Block 9 Centenary City, Abakaliki | 3020118 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 60000000 | 60000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Purchase of 2nos. Towing van @ 80,000,000.00 | 23010106 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 160000000 | 160000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Installation of 100No.road signs @ 80,000 | 23020118 | Procurement | Works | Direct Procurement (DP) |  | State Budget |  | 8000000 | 8000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 6months
Landscaping of block 9 centenary city | 3020118 - | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 20000000 | 20000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of Ezillo-Ezzagu (21.288km) | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 3000000000 | 3000000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of Owutu-Ekenta IateUgwufie - Ekata - Letu Road, Edda (CCD) | 23020114 - | Procurement | Works | Direct Procurement (DP) |  | State Budget | AFIKPO SOUTH EDDA | 2000000000 | 2000000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of Ezillo- Amanze internal road | 3020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ISHIELU | 2000000000 | 2000000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of Isu- Ezzagu- Enugu road | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ONICHA | 2000000000 | 2000000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
Construction of Iziogo- Onuenyim Road (12km) | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | EBONYI | 2000000000 | 2000000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of Ubamiri- Rounder road | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | IZZI | 2000000000 | 2000000000 | Fixed price contract | 4th Sept 2025 | 3rd oct 2025 | 3rd oct 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 9th oct 2025 | 9th oct 2025 | 12 Months
Construction of Ndiofutu- Agalegu Road | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | IZZI | 2000000000 | 2000000000 | Fixed price contract | 4th Sept 2025 | 3rd oct 2025 | 3rd oct 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 9th oct 2025 | 9th oct 2025 | 12 Months
Construction of Onuakpara- Azuoffia Road | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | EBONYI | 2000000000 | 2000000000 | Fixed price contract | 13th Feb 2025 | 14th March 2025 | 14th March 2025 |  |  |  | 20th March 2025 | 20th March 2025 | 20th March 2025 | 24th march 2025 | 26th march 2025 | 12 Months
Construction of Odumoke - Egudenagu Road | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | EBONYI | 2000000000 | 2000000000 | Fixed price contract | 1st July 2025 | 30th July 2025 | 30th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Months
Construction of Amuzu Igbeagu- NdidokoAmeka Ro | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | IZZI | 2000000000 | 2000000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of 1No. Tunnel at Vanco Junction to Old Abakpa Market | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | State Wide | 12000000000 | 12000000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 14th oct 2025 |  | 12 Months
Construction of 1no. flyover at Vanco Junction to Union Bank junction | 23020114 | Procurement | Works | Direct Procurement (DP) |  | State Budget | ABAKALIKI | 3000000000 | 3000000000 | Fixed price contract | 5th Jan 2025 | 5th feb 2025 | 5th feb 2025 |  |  |  | 8th feb 2025 | 8th feb 2025 | 8th feb 2025 |  |  | 12 Months