## Sheet1
Procuring Entity and Disposing Entity (MDA) | Ministry of Housing and Urban Development
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FIRST QUARYER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
COMPLETION OF CENTENARY CITY SECRETARIAT | 23020104 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 150000000 | 150000000 | Fixed price contract | 8th Jan 2025 | 6th feb. 2025 | 6th feb. 2025 |  |  |  | 10th Feb 2025 | 12th May 2025 | 12th feb 2025 |  |  | 12 Month
Rehabilitation of Ecumenical Centre | 23030103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 20000000 | 20000000 | Fixed price contract | 8th April 2025 | 7th May 2025 | 7th May 2025 |  |  |  | 12th May 2025 | 12th May 2025 | 14th may 2025 | 16th may 2025 | 19th may 2025 | 12 Month
Her Excellency's New office (Rehabilitation) | 23030121 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 30000000 | 30000000 | Fixed price contract | 2nd june 2025 | 1st July 2025 | 1st July 2025 |  |  |  | 8th jJuly 2025 | 8th jJuly 2025 | 14th July 2025 | 17th July 2025 | 17th July 2025 | 12 Month
Internal and External fencing of the New Government House | 23020118 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 20000000 | 20000000 | Fixed price contract | 4th Aug.2025 | 2nd Sept. 2025 | 2nd Sept. 2025 |  |  |  | 8th sept.2025 | 8th sept.2025 | 8th sept.2025 | 15th Sept 2025 | 15th Sept 2025 | 12months
Rehabilitation of Gate Houes at Governor's Office, Governor's Lodge and Presidentia Lodge | 23030103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 10000000 | 10000000 | Fixed price contract | 1st July 2-025 | 130th July 2025 | 130th July 2025 |  |  |  | 6th Aug.2025 | 6th Aug.2025 | 6th Aug. 2025 | 11th Aug.2025 | 11th Aug.2025 | 12 Month
Rehabilitation of new Government House Chapel & Banquet Hall | 23030103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 50000000 | 50000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Month
Construction of one Storey Building at new Prison extension Block A1 2No | 23020104 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Abakaliki | 150000000 | 150000000 | Fixed price contract | 26th Aug 2025 | 25th Sept. 2025 | 25th Sept. 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 8th oct 2025 | 10th oct 2025 | 12months