## Sheet1
Procuring Entity and Disposing Entity (MDA) | MINISTRY OF WATER RESOURCES
Procuring Entity and Disposing Entity (LGAs) | EBONYI
Procurement Plan for financial year | 2025
Date Last Updated | FISRT QUARTER
Comments
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Construction of ongoing Ivo Water Scheme project | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | IVO | 300000000 | 300000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Procurement of water treatment chemicals for Ezillo, Old Abakaliki, Oferekpe and Ivo water schemes. | 23020116 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | IVO | 300000000 | 300000000 | Fixed price contract | 4th feb.. 2025 | 5th march 2025 | 5th March. 2025 |  |  |  | 10th March.2025 | 10th March.2025 | 10th March.2025 | 17th march 2825 | 19th march 2825 | 12 Months
Rehabilitation of water pipelines in Abakaliki Capital Territory. | 23030104 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 500000000 | 500000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Reticulation of water in Edda (Izicha) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Edda | 100000000 | 100000000 | Fixed price contract | 4th feb.. 2025 | 5th march 2025 | 5th March. 2025 |  |  |  | 10th March.2025 | 10th March.2025 | 10th March.2025 | 17th march 2825 | 19th march 2825 | 12 Months
Re-construction of collapsed staff quarters at Ezillo water scheme | 23030103 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Ishielu | 50000000 | 50000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Procurement of water Equipment for laboratory samples/Test | 23010139 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 50000000 | 50000000 | Fixed price contract | 3rd march 2025 | 2nd April 2025 | 2nd April 2025 |  |  |  | 8th April 2025 | 8th April 2025 | 8th April 2025 | 10th April 2025 | 14th April 2025 | 12months
Completion of Ukawu Water scheme project (Civil works). | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget |  | 50000000 | 50000000 | Fixed price contract | 1st Sept 2025 | 30th Sept 2025 | 30th Sept 2025 |  |  |  | 6th Oct.2025 | 6th Oct.2025 | 6th Oct.2025 | 10th Oct 2025 | 13th Oct 2025 | 12 Months
Construction of Iboko water Reservoir | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | EBONYI | 13000000 | 13000000 | Fixed price contract | 6th Jan.2025 | 5th Feb 2025 | 5th Feb 2025 |  |  |  | 11th feb 2025 | 11th feb 2025 | 11th feb 2025 | 13th feb 2025 | 13th feb 2025 | 12months
Construction of perimeter fence at Ezillo Water Scheme. | 23020105 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | EBONYI | 30000000 | 30000000 | Fixed price contract | Jan 8th 2025 | 7th feb. 2025 | 7th feb. 2025 |  |  |  | 13th Feb 2025 | 13th Feb 2025 | 13th Feb 2025 | 14th Feb 2025 | 14th Feb 2025 | 12 months
Water reticulation at Obulechi health centre in Akpe Amachi community in Abakaliki, Ebonyi North (CCD) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Outside State | 25000000 | 25000000 | Fixed price contract | Jan 3rd 2025 | 3rd feb 2025 | 3rd feb 2025 |  |  |  | 10th feb 2025 | 10th feb 2025 | 10th feb 2025 | 11th feb 2025 | 11th feb 2025 | 6months
Water reticulation at Ezekuna, Anyim, Anyinato Primary School, Ohinya village Idembia Community Ezza North (CCD) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 25000000 | 25000000 | Fixed price contract | 3rd march 2025 | 2nd April 2025 | 2nd April 2025 |  |  |  | 8th April 2025 | 8th April 2025 | 8th April 2025 | 10th April 2025 | 14th April 2025 | 6months
Water reticulation in Ozizza Health Centre in Ibii/Ozizza community Afikpo North (CCD) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 30000000 | 30000000 | Fixed price contract | 1st may 2025 | 30th may 2025 | 30th may 2025 |  |  |  | 5th June 2025 | 5th June 2025 | 6th june 2025 | 9th june 2025 | 11th june 2025 | 6months
partnership fund for Spin project(world Bank Assisted | 23020105 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 200000000 | 200000000 | Fixed price contract | 1st july 2025 | 30th july 2025 | 30th july 2025 |  |  |  | 4th Aug 2025 | 4th Aug 2025 | 4th Aug 2025 | 6th Aug 2025 | 8th Aug 2025 | 6months
Sanitation and Hygiene awareness programme | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 20000000 | 20000000 | Fixed price contract | 2nd july 2025 | 31st july 2025 | 31st july 2025 |  |  |  | 1st Aug 2025 | 1st Aug 2025 | 5th Aug 2025 | 5th Aug 2025 | 7th Aug 2025 | 6months
Construction of store for water Equipment | 23020104 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | IKWO | 50000000 | 50000000 | Fixed price contract | 4th Aug 2025 | 3rd Sept 2025 | 3rd Sept 2025 |  |  |  | 9th Sept 2025 | 9th Sept 2025 | 12th Sept 2025 | 15th oct 2025 | 17th Oct 2025 | 6months
Mapping of site for the takeoff of water cooperation in the State | 23050101 | Procurement | Services | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 100000000 | 100000000 | Fixed price contract | 2nd Oct 2025 | 31st oct 2025 | 31st oct 2025 |  |  |  | 7th Nov 2025 | 7th Nov 2025 | 7th Nov 2025 | 10th Nov 2025 | 10th Nov 2025 | 6months
Drilling and installation of water boreholes in the strategic places of 7 wards in Abakaliki South Constituency of Ebonyi State (constituency project) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 42000000 | 42000000 | Fixed price contract | 3rd Nov 2025 | 2nd Dec 2025 | 2nd Dec 2025 |  |  |  | 8th Dec 2025 2025 | 8th Dec 2025 2025 | 8th Dec 2025 2025 | 10th Dec 2025 | 12th Dc 2025 | 6months
Installation of water borehole in Unwana A – Ezi Oti Inya, Unwana B – Amaekwu, Itim Mgbom-Ezi Ukwu, Ohaisu A – Ngodo, Ohaisu B – Amangballa, Ugwuegu – Ezi Ugwu and Nkpoghoro – Ezi Nwachi of the 7 wards of my Constituency (constituency project) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 40000000 | 40000000 | Fixed price contract | 2nd June 2025 | 1st july 2025 | 1st july 2025 |  |  |  | 7th July 2025 | 7th July 2025 | 7th July2025 | 9th july 2025 | 10th july 2025 | 6months
Drilling and installation of water boreholes in the 6 wards of Edda East Constituency viz: Amaigbo ward, Amangwu ward, Amoso ward, Ogbu ward, Oso ward, Owutu ward (constituency project). | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | ISHIELU | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months
Drilling of boreholes; Akahu-Uhwu Omege, Ngamgbo Ohinya Azuituma, Ogharugo Ndeguazu, Ofuewu, Ngamgbo Okposi, Ngamgbo Ucha, Etegidigwe Oshegbe, Uwhumba Ishiachi Village, Unuzo Nwalo, Ngamgbo Umuezeoka, Igbuwhu Umuezeoka and Ngamgbo Evara Omege (constituency project). | 23020105 | Procurement | Supplies | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months
Drilling and installation of water boreholes in favour of the 6 wards in my constituency thus; Oriuzor, Ekka, Ogboji, Nkomoro, Inyere and Amuda/Amawula wards (constituency project). | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months
Drilling and installation of water boreholes in the 11 wards of Ezza South Constituency viz: Umunwagu Idembia Ward, Ikwuato Idembia Ward, Echara Ward, Amudo/Okofia Ward, Ezzama Ward, Amuzu Ward, Ameka ward, Amana Ward, Amaezekwe ward, Amegu/Nsokkara ward, Onueke Urban ward (constituency project | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months
Drilling and installation of boreholes in the 7 wards in my constituency which includes: Mgbalukwe ward 1, Mgbalukwe 2, Igbaegu ward 1, Igbaegu ward 2, Igbaegu ward 3, Ndieze ward 1, Ndieze ward 2 respectively (constituency project). | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget |  | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months
Drilling and installation of water boreholes in favour of the seven wards in my constituency as thus Mgbo Agbaja, Enyanwu-igwe, Offia Onwe, Igbuhu, Ndiagu, Igweledeoha and Iziogo wards (constituency project) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months
Drilling and installation of water boreholes in the 7 wards of Ohaozara East Constituency viz: Amaechi ward, Ene-na Ezeraku, Achara ward, Mgbom Okposi, Okposi Okwu ward, Ugbogologo ward and Uhuotaru ward (constituency project) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget |  | 40000000 | 40000000 | Fixed price contract | 20th may 2025 | 19th june 2025 | 19th june 2025 |  |  |  | 24th june 2025 | 24th june 2025 | 24th june 2025 | 26th june 2025 | 26th june 2025 | 6months