## Sheet1
|  |  |  | EBONYI STATE RURAL WATER SUPPLY SANITATION AGENCY | [5 empty] | ( | EB-RUWASSA |  | )
Project Description | Reference No./Package No./File No./Budget Code | Process Type | Category | Procurement / Disposal Method | Quantities | Source of Funds | Location | Budgetary Provision in Naira | Approved Contract sum (Naira) | Contract Type | Advertisement date/Call for EoI | Bid Closing / Opening date | Bid Evaluation Date | Issuance of No objection Certificate | Vetting of Contracts Documents Date | Selection Notificat ion Date | Contract Offer Date | Contract Signing Date | Award Notification Date | Project Mobilization Date | Project Commencement Date | Completion date
Purchase of 1 No Tarameter Geological Survey equipment. | 23010133 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget |  | 8000000 | 8000000 | Fixed price contract | 27th jan 2025 | 26th feb 2025 | 26th feb 2025 |  |  |  | 4th march 2025 | 4th march 2025 | 5th march 2025 | 10th march 2025 | 13th march 2025 | 6months
Purchase of 1 No Global Positioning System (GPS) | 23020116 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | ABAKALIKI | 2000000 | 2000000 | Fixed price contract | 27th jan 2025 | 26th feb 2025 | 26th feb 2025 |  |  |  | 4th march 2025 | 4th march 2025 | 5th march 2025 | 10th march 2025 | 13th march 2025 | 3 months
Repairs / Rehabilitation of 120 No Non - functional boreholes across the 13 LGAs of Ebonyi State. | 23030104 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | State Wide | 130000000 | 130000000 | Fixed price contract | 27th jan 2025 | 26th feb 2025 | 26th feb 2025 |  |  |  | 4th march 2025 | 4th march 2025 | 5th march 2025 | 10th march 2025 | 13th march 2025 | 6months
Construction of 2No. Solar powered boreholes in South Senatorial Zone (CCD) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | South Zone | 130000000 | 130000000 | Fixed price contract | 27th jan 2025 | 26th feb 2025 | 26th feb 2025 |  |  |  | 4th march 2025 | 4th march 2025 | 5th march 2025 | 10th march 2025 | 13th march 2025 | 6months
Construction of 2No. Solar powered boreholes at Central Senatoral Zone (CCD) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | Central Zone | 20000000 | 20000000 | Fixed price contract | 27th jan 2025 | 26th feb 2025 | 26th feb 2025 |  |  |  | 4th march 2025 | 4th march 2025 | 5th march 2025 | 10th march 2025 | 13th march 2025 | 6months
Construction of 2No. Solar powered boreholes at North Senatoral Zone (CCD) | 23020105 | Procurement | Works | Open Domestic Bidding (ODB) |  | State Budget | North Zone | 20000000 | 20000000 | Fixed price contract | 27th jan 2025 | 26th feb 2025 | 26th feb 2025 |  |  |  | 4th march 2025 | 4th march 2025 | 5th march 2025 | 10th march 2025 | 13th march 2025 | 6months